## Eastin Block
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
Weekly Meeting | 2026-01-22 | 2026-01-22 | -90 | 2026-01-22 | 1
Week of January 26, 2026
Weekly Meeting | 2026-01-29 | 2026-01-29 | -83 | 2026-01-29 | 1
Week of February 1, 2026
Meeting | 2026-02-03 | 2026-02-03 | -5 | 2026-02-03 | 1
Database Testing | 2026-02-03 | 2026-02-10 | 2 |  | -1
Week of February 8, 2026
Meeting | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
Week of February 15th
weekly meeting | 2026-02-19 | 2026-02-19 | -62 | 2026-02-19 | 1
Week of February 22, 2026
Weekly Meeting | 2026-02-26 | 2026-02-26 | 5 | 2026-02-26 | 1
Test Database Structure and Dependency | 2026-02-26 | 2026-03-05 | 5 |  | -1
Test Database Table Elements | 2026-02-26 | 2026-03-05 | 5 |  | -1
Week of March 8, 2026
Weekly Meeting | 2026-03-10 | 2026-03-10 | -8 | 2026-03-10 | 1
Figure out compilation issues for the database and QA_TEST folder to report to dev | 2026-03-14 | 2026-03-14 | -4 | 2026-03-14 | 1
Test Database Structure and Dependency | 2026-03-10 | 2026-03-19 | 1 |  | -1
Test Database Table Elements | 2026-03-10 | 2026-03-19 | 1 |  | -1
Week of March 15th
Weekly Meeting | 2026-03-19 | 2026-03-19 | -3 |  | -1
Test Database Structure and Dependency | 2026-03-10 | 2026-03-19 | -3 |  | -1
Test Database Table Elements | 2026-03-10 | 2026-03-19 | -3 |  | -1
Week of March 22nd
Test Database Structure and Dependency | 2026-03-10 | 2026-03-26 | 4 |  | -1
Test Database Table Elements | 2026-03-10 | 2026-03-26 | 4 |  | -1
Test General Programming Requirements | 2026-03-22 | 2026-03-26 | 4 |  | -1
Week of March 29th
Test Pet Page for bugs | 2026-04-01 | 2026-04-09 | 5 | 2026-04-02 | 1
Week of April 5th
Test PetMain.cs | 2026-04-07 | 2026-04-11 | -11 | 2026-04-12 | 1
Test EditPet.cs | 2026-04-07 | 2026-04-11 | -11 | 2026-04-12 | 1
Week of April 12th
Final testing for any critical bugs in system | 2026-04-12 | 2026-04-15 | -7 | 2026-04-15 | 1
Check schema matches database structure | 2026-04-15 | 2026-04-21 | -1 | 2026-04-22 | 1
Check/Test Installation Guide | 2026-04-15 | 2026-04-21 | -1 | 2026-04-20 | 1
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Alyssa Lilly
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 2026
Weekly Meeting | 2026-01-22 | 2026-01-22 | -90 | 2026-01-22 | 1
Week of January 26, 2026
Weekly Meeting | 2026-01-29 | 2026-01-29 | -83 | 2026-01-29 | 1
Week of February 1st 2026
Weekly meeting attendance | 2026-02-03 | 2026-02-03 | -5 | 2026-02-03 | 1
Testing Events Folder Files | 2026-02-03 | 2026-02-10 | 7 | 2026-02-08 | 1
Week of February 8th 2026
Weekly meeting attendance | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
Week of February 15th 2026
Weekly meeting attendance | 2026-02-19 | 2026-02-19 | -62 |  | -1 | Missed meeting due to illness
Database Testing For Sprint 2 - Found not Possible | 2026-02-19 | 2026-03-09 | -44 | 2026-02-26 | 1
Week of February 22nd 2026
Weekly meeting attendance | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Installed all necessary programs for DB | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Researched TSQLT - Attempted Startup | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Testing for Sprint 2 Changed to Stored Procedures | 2026-02-26 | 2026-03-09 | 9 |  | -1
Week of March 8th 2026
Weekly meeting attendance | 2026-03-10 | 2026-03-10 | -7 | 2026-03-10 | 1
Testing GUI - Visual Appearance Check-In | 2026-03-10 | 2026-03-19 | 2 |  | -1
Testing GUI - Components Check-In | 2026-03-10 | 2026-03-19 | 2 |  | -1
Testing GUI - Visual Appearance Final Version | 2026-03-10 | 2026-03-26 | 9 |  | -1
Testing GUI - Components Final Version | 2026-03-10 | 2026-03-26 | 9 |  | -1
Week of March 15th 2026
Weekly meeting attendance | 2026-03-19 | 2026-03-19 | -3 | 2026-03-19 | 1
Testing GUI - Visual Appearance Check-In | 2026-03-10 | 2026-03-19 | -3 | 2026-03-19 | 1
Testing GUI - Components Check-In | 2026-03-10 | 2026-03-19 | -3 | 2026-03-19 | 1
Displayed and Described Graphic Designer's Inputs | 2026-03-19 | 2026-03-19 | -3 | 2026-03-19 | 1
Met with Graphic Design Team | 2026-03-18 | 2026-03-18 | -4 | 2026-03-18 | 1
Week of March 22th 2026
Weekly meeting attendance | 2026-03-26 | 2026-03-26 | -9 | 2026-03-26 | 1
Testing GUI - Components Final Version | 2026-03-10 | 2026-03-26 | -9 | 2026-03-24 | 1
Testing of Calendar Screen | 2026-04-02 | 2026-04-02 | -20 | 2026-03-29 | 1
Week of March 29th 2026
Weekly meeting attendance | 2026-03-31 | 2026-03-31 | -22 | 2026-03-31 | 1
Testing of Calendar Screen - V8.1 of DB | 2026-03-31 | 2026-04-09 | -13 | 2026-04-07 | 1
Week of April 5th 2026
Weekly meeting attendance | 2026-04-07 | 2026-04-07 | -15 | 2026-04-07 | 1
Testing of V10 of DB | 2026-04-07 | 2026-04-14 | -8 | 2026-04-14 | 1
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Madison Koscielski
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
Weekly Meeting | 2026-01-22 | 2026-01-22 | -90 | 2026-01-22 | 1
Week of January 26, 226
Weekly Meeting | 2026-01-29 | 2026-01-29 | -83 | 2026-01-29 | 1
Week of February 1st
Weekly Meeting | 2026-02-03 | 2026-02-03 | -78 | 2026-02-03 | 1
SqlClientManager | 2026-02-08 | 2026-02-10 | -71 |  | -1 | Communications from dev revealed this file was a template and not necessary for production. No further action on this item is required.
Week of February 8th
weekly meeting | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
take meeting minutes | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
Week of February 15th
weekly meeting | 2026-02-19 | 2026-02-19 | -62 | 2026-02-19 | 1
Week of Febraury 22nd
weekly meeting | 2026-02-26 | 2026-02-26 | -55 | 2026-02-26 | 1
take meeting minutes | 2026-02-26 | 2026-02-26 | -55 |  | -1
Create Unit Tests For 53 Stored Procedures | 2026-02-23 | 2026-02-28 | -53 |  | -1
Did Research on SQL Injection Testing | 2026-02-25 | 2026-02-28 | -53 | 2026-02-25 | 1
Created a guide on how to install and use tSQLt for unit testing | 2026-02-26 | 2026-02-28 | -53 | 2026-02-27 | 1
Week of March 8th
Attended Weekly Meeting | 2026-03-10 | 2026-03-10 |  | 2026-03-10 | 1
Had a discussion with Devs Database team about issues found in last weeks testing | 2026-03-10 | 2026-03-10 |  | 2026-03-10 | 1
Had a discussion with Devs Database team about tSQLt unit testing | 2026-03-10 | 2026-03-10 |  | 2026-03-10 | 1
Week of March 15th
Attended Weekly Meeting |  | 2026-03-19 |  | 2026-03-19 | 1
Write new tSQLt unit tests for new stored procedures | 2026-03-16 | 2026-03-19 |  | 2026-03-22 | 1
Update previous tSQLt unit tests to account for table changes | 2026-03-16 | 2026-02-19 |  | 2026-03-18 | 1
Week of March 22nd
Attended Weekly Meeting
Documented Tests for Sprint 3.5 | 2025-03-23 | 2026-03-26 |  | 2026-03-23 | 1
Week of March 29th | [5 empty] | I am having a tendonitis flare up in my wrists which makes typing painful. I have been slower and have braces on my wrists. I have a doctors note if requested -Madison
Updated Get Stored Procedure Unit Tests For DB Version 8 | 2026-03-30 | 2026-04-04 |  | 2026-04-02 | 1
Ran Unit Tests for Get Stored Procedures = no bugs found | 2026-04-02 | 2026-04-04 |  | 2026-04-02 | 1
Week of April 5th
Update Get Stored Procedure Unit Tests For DB Version 9: Total 70 | 2026-04-08 | 2026-04-11 |  | 2026-04-10 | 1
Update Create Stored Procedure Unit Tests For DB Version 9 | 2026-04-10 | 2026-04-11 |  |  | -1
Update Delete Stored Procedure Unit Tests For DB Version 9 |  | 2026-04-11 |  |  | -1
Update Edit Stored Procedure Unit Tests For DB Version 9 |  | 2026-04-11 |  |  | -1
Update Add Stored Procedure Unit Tests For DB Version 9: Total 3 |  | 2026-04-11 |  |  | -1
Update Misc Stored Procedure Unit Tests For DB Version 9 |  | 2026-04-11 |  |  | -1
Create new GET stored procedure unit tests for DB Version 9: Made 21 | 2026-04-10 | 2026-04-11 |  | 2026-04-10 | 1
Create new ADD stored procedure unit tests for DB Version 9: Made 8 | 2026-04-10 | 2026-04-11 |  | 2026-04-10 | 1
Week of April 12th
Update Get Stored Procedure Unit Tests for DB Version 10 | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Update Create Stored Procedure Unit Tests For DB Version 10 | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Update Delete Stored Procedure Unit Tests For DB Version 10 | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Update Edit Stored Procedure Unit Tests For DB Version 10 | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Update Add Stored Procedure Unit Tests For DB Version 10 | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Update Misc Stored Procedure Unit Tests For DB Version 10 | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Total Tests Modified and Run: 141 | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Removed unit tests that didn't reflect the same schema from ver 9 & some edge cases in favor of time. 141 unit tests now vs 193 mid march | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Created a pull request with updated files | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Documented all tests in a singular test line | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | 1
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Rosh Mizoory
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
Weekly Meeting | 2026-01-22 | 2026-01-22 | -90 | 2026-01-22 | 1
Week of January 26, 2026
Weekly Meeting | 2026-01-29 | 2026-01-29 | -83 | 2026-01-29 | 1
Week of February 1st, 2026
Created and pushed tests for VetVisits and Vaccines | 2026-02-05 | 2026-02-05 | -76 | 2026-02-05 | 1
Cleaned and formatted the test section in QA Doc Suggestions | 2026-02-05 | 2026-02-05 | -76 | 2026-02-05 | 1
Continued cleaning up the group folder and fixed the bug tab in QA Doc Suggestions | 2026-02-06 | 2026-02-06 | -75 | 2026-02-06
Weekly Meeting | 2026-02-03 | 2026-02-03 | -78 |  | -1 | Rosh did not attend the meeting, but he let me know beforehand
Week of February 8th, 2026
Weekly meeting attendance (Monday) | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
Fixed and updated the QA Doc Suggestions file then deleted the bug section and combined it with tests to avoid confusion. Also spoke to members of dev about changes we could make inorder to make information more accessible to their team. | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
Created Bug History tab in QA Doc and added missing information. | 2026-02-12 | 2026-02-12 | -69 | 2026-02-12 | 1
Week of February 15th
weekly meeting | 2026-02-19 | 2026-02-19 | -62 | 2026-02-19 | 1
Week of February 22nd, 2026
Weekly meeting attendance (Thursday) | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Started testing DB for correct implementation of stored procedures | 2026-02-26 | 2026-02-26 | -2 |  | -1
Week of March 1st, 2026
Finished testing DB for correct implementation of stored procedures, verified reset workflow, and submitted QA pull request as well as creating PR for QA_Testing_Rosh | 2026-03-01 | 2026-03-01 | -16 | 2026-03-01 | 1
Weekly meeting attendance (Thursday) | 2026-03-05 | 2026-03-05 | -12 | 2026-03-05 | 1
Week of March 8th, 2026
Weekly meeting attendance (Tuesday) | 2026-03-08 | 2026-03-08 | -9 | 2026-03-08 | 1
Added Sprint 4 tab to Excel and verified that bugs were correctly placed into bug history tab | 2026-03-14 | 2026-03-14 | -3 | 2026-03-14 | 1
Began working on sprint 4 - Database/Data - Connection of DB to Application, Roles, SQL Injection | 2026-03-14 | 2026-03-14 | -3 |  | -1
Week of March 15th, 2026
Weekly meeting attendance (Tuesday) | 2026-03-19 | 2026-03-19 | -3 | 2026-03-19 | 1
Created and Pushed Tests for FileRecordHelper.cs | 2026-03-20 | 2026-03-20 | -2 | 2026-03-20 | 1
Created and Pushed Tests for FolderHelper.cs | 2026-03-20 | 2026-03-20 | -2 | 2026-03-20 | 1
Created and Pushed Tests for MedicalHelpers.cs | 2026-03-20 | 2026-03-20 | -2 | 2026-03-20 | 1
Created and Pushed Tests for LoginHelper.cs | 2026-03-20 | 2026-03-20 | -2 | 2026-03-20 | 1
Created and Pushed Tests for UIHelpers.cs | 2026-03-20 | 2026-03-20 | -2 | 2026-03-20 | 1
Week of March 22nd, 2026
Weekly meeting attendance (Thursday) | 2026-03-26 | 2026-03-26 | -9 | 2026-03-26 | 1
Began general requirements testing | 2026-03-28 | 2026-03-28 | -7 |  | -1
Week of March 29th, 2026
General requirements manual tests | 2026-03-29 | 2026-03-29 | -6 | 2026-03-29 | 1
General requirements manula tests | 2026-03-30 | 2026-03-30 | -5 | 2026-03-30 | 1
Week of April 5th, 2026
Weekly meeting attendance (Tuesday) | 2026-04-07 | 2026-04-07 | -15 | 2026-04-07 | 1
Manual tests, Sprint 5 - DB V9 (Exclusively looking for and reporting bugs) | 2026-04-07 | 2026-04-07 | -15 | 2026-04-07 | 1
Manual tests, Sprint 5 - DB V9 (Exclusively looking for and reporting bugs) | 2026-04-08 | 2026-04-08 | -14 | 2026-04-08 | 1
Week of April 12th, 2026
Manual tests, Sprint 5 - DB V10 (Exclusively looking for and reporting bugs) | 2026-04-13 | 2026-04-13 | -9 | 2026-04-13 | 1
Manual tests, Sprint 5 - DB V10.1 (Exclusively looking for and reporting bugs) | 2026-04-15 | 2026-04-15 | -7 | 2026-04-15 | 1
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Jacob Riedel
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
Weekly Meeting | 2026-01-22 | 2026-01-22 | -90 | 2026-01-22 | 1
Week of January 26, 2026
Weekly meeting | 2026-01-29 | 2026-01-29 | -83 | 2026-01-29 | 1
Week of February 1, 2026
Attended Meeting | 2026-02-03 | 2026-02-03 | -6 | 2026-02-03 | 1
Created tests for home folder files | 2026-02-03 | 2026-02-10 | 1 |  | -1
Week of February 8, 2026
Attended meeting | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
Week of February 15, 2026
Attended meeting | 2026-02-19 | 2026-02-19 | -9 | 2026-02-19 | 1
Created tests for FileRecord.cs | 2026-02-19 | 2026-02-28 | -53 |  | -1
Created tests for Folder.cs | 2026-02-19 | 2026-02-28 | -53 |  | -1
Created tests for Expense.cs | 2026-02-19 | 2026-02-28 | -53 |  | -1
Created tests for Revenue.cs | 2026-02-19 | 2026-02-28 | -53 |  | -1
Week of February 22, 2026
Attended meeting | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Created tests for FileRecord.cs | 2026-02-19 | 2026-02-28 | 0 |  | -1
Created tests for Folder.cs | 2026-02-19 | 2026-02-28 | 0 |  | -1
Created tests for Expense.cs | 2026-02-19 | 2026-02-28 | 0 |  | -1
Created tests for Revenue.cs | 2026-02-19 | 2026-02-28 | 0 |  | -1
Week of March 1, 2026
Missed teams meeting (Spring break) | 2026-03-05 | 2026-03-05 | -12 |  | -1
Created tests for FileRecord.cs | 2026-02-19 | 2026-03-09 | -8 | 2026-03-07 | 1
Created tests for Folder.cs | 2026-02-19 | 2026-03-09 | -8 | 2026-03-07 | 1
Created tests for Expense.cs | 2026-02-19 | 2026-03-09 | -8 | 2026-03-07 | 1
Created tests for Revenue.cs | 2026-02-19 | 2026-03-09 | -8 | 2026-03-07 | 1
Week of March 8, 2026
Attended meeting | 2026-03-10 | 2026-03-10 | -25 | 2026-03-10 | 1
Investigated DB issues on personal machine | 2026-03-12 | 2026-03-12 | -23 | 2026-03-31 | 1
Unit testing scrapped in favor of manual tests | 2026-03-12 | 2026-03-12 | -23 |  | -1
Week of March 15, 2026
Attended meeting | 2026-03-19 | 2026-03-19 | -16 | 2026-03-19 | 1
Investigated DB issues on personal machine | 2026-03-12 | 2026-03-12 | -23 | 2026-03-31 | 1
Unit testing scrapped in favor of manual tests | 2026-03-12 | 2026-03-12 | -23 |  | -1
Week of March 22, 2026
Attended meeting | 2026-03-19 | 2026-03-19 | -16 | 2026-03-19 | 1
Investigated DB issues on personal machine | 2026-03-12 | 2026-03-12 | -23 | 2026-03-31 | 1
Performed manual testing on pets screen | 2026-03-29 | 2026-04-02 | -2 |  | -1
Week of March 29, 2026
Attended meeting | 2026-03-19 | 2026-03-19 | -34 | 2026-03-19 | 1
Investigated and finally fully solved DB issues on personal machine | 2026-03-12 | 2026-03-12 | -41 | 2026-03-31 | 1
Performed manual testing on pets screen | 2026-03-29 | 2026-04-02 | -20 | 2026-04-02 | 1
Week of April 5, 2026
Performed final tests before install | 2026-04-05 | 2026-04-15 | -7 | 2026-04-14 | 1
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Bowen Steinke
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
Weekly meeting | 2026-01-22 | 2026-01-22 | -90 |  | -1 | Unable to attend, but let group know in advance.
Week of January 26, 2026
Attended QA weekly meeting | 2026-01-29 | 2026-01-29 | -83 | 2026-01-29 | 1
Explored class's GitHub Repo | 2026-01-29 | 2026-01-29 | -83 | 2026-01-29 | 1
QA/Dev workflow | 2026-01-29 | 2026-02-02 | -79 | 2026-02-02 | 1
Week of February 2, 2026
Weekly meeting | 2026-02-03 | 2026-02-03 | -78 | 2026-02-03 | 1
Set up QA Testing Branch | 2026-02-03 | 2026-02-05 | -76 | 2026-02-04 | 1
Tested People files (Person & Volunteer) | 2026-02-03 | 2026-02-10 | -71 | 2026-02-10 | 1
Week of February 8, 2026
Weekly meeting | 2026-02-09 | 2026-02-09 | -72 | 2026-02-09 | 1
Reported tests | 2026-02-09 | 2026-02-13 | -68 | 2026-02-11 | 1
Merged QA team member PRs to QA_Testing_Branch | 2026-02-09 | 2026-02-15 | -66 | 2026-02-14 | 1
Week of February 15th
weekly meeting | 2026-02-19 | 2026-02-19 | -62 | 2026-02-19 | 1
Merged Sprint 2 into QA Testing Branch | 2026-02-19 | 2026-02-19 | -62 | 2026-02-19 | 1
Merged QA Testing Branch into new QA Sprint1 branch | 2026-02-19 | 2026-02-19 | -62 | 2026-02-19 | 1
Week of February 23rd
weekly meeting | 2026-02-26 | 2026-02-26 | -55 | 2026-02-26 | 1
Started Manual Testing on PeopleMain.cs and CreateEditPeople.cs | 2026-02-19 | 2026-03-05 | -48 | 2026-03-05 | 1
Review GUI requirements | 2026-02-28 | 2026-03-21 | -32 |  | -1 | switched to general requirements for time being (3/21)
Review Button and Card component files | 2026-02-26 | 2026-03-05 | -48 | 2026-03-05 | 1
Week of March 8
Merge sprint 3 | 2026-03-10 | 2026-03-10 | -43 | 2026-03-10 | 1
Store sprint 2 tests in new branch | 2026-03-10 | 2026-03-10 | -43 | 2026-03-10 | 1
weekly meeting | 2026-03-10 | 2026-03-10 | -43 | 2026-03-10 | 1
worked with dev to merge first part of sprint 4 | 2026-03-12 | 2026-03-12 | -41 | 2026-03-12 | 1
Reviewed button styling components | 2026-03-10 | 2026-03-21 | -32 | 2026-03-11 | 1
Week of March 15
Weekly Meeting | 2026-03-19 | 2026-03-19 | -34 | 2026-03-19 | 1
Reviewed General Requirements 1-25 | 2026-03-17 | 2026-03-21 | -32 | 2026-03-21 | 1
Communicated with Doc on questions about ambiguous tests | 2026-03-21 | 2026-03-21 | -32 | 2026-03-21 | 1
Created/Recorded tests for 19 requirements I could test | 2026-03-21 | 2026-03-21 | -32 | 2026-03-23 | 1 | Still working on adding tests to spreadsheet and making git issues - finished (3/23/26)
Created document with issues/inconsistencies with UI (not bugs) | 2026-03-21 | 2026-03-21 | -32 | 2026-03-21 | 1
Tested login screen and user.cs | 2026-03-17 | 2026-03-21 | -32 | 2026-03-21 | 1
Week of March 22
Reviewed Requirements 25-45 | 2026-03-24 | 2026-03-28 | -25 | 2026-03-28 | 1
Communicated critical features for system: session timeout feature, scroll bars, object ownership (house, pet, person) | 2026-03-28 | 2026-03-28 | -25 | 2026-03-28 | 1
updated/merged branches from sprint 5 to qa test branch | 2026-03-28 | 2026-03-28 | -25 | 2026-03-28 | 1 | Multiple times throughout the week
Week of March 29
Reviewed MDARD Compliance laws | 2026-03-30 | 2026-04-04 | -18 | 2026-04-02 | 1
Communicated issues with dev | 2026-03-30 | 2026-04-04 | -18 | 2026-04-04 | 1 | Multiple times throughout the week
Week of April 5
Communicated finances issue with Dev and helped fix | 2026-04-05 | 2026-04-12 | -10 | 2026-04-12 | 1 | Multiple times throughout the week
Weekly meeting/huddle | 2026-04-07 | 2026-04-07 | -15 | 2026-04-07 | 1
Picked up server | 2026-04-10 | 2026-04-10 | -12 | 2026-04-10 | 1
Meeting with Carson to set up server | 2026-04-11 | 2026-04-12 | -10 | 2026-04-11 | 1
Tested files and pet creation while connected to server | 2026-04-11 | 2026-04-12 | -10 | 2026-04-12 | 1
Week of April 12
Tested files, pets, homes, and person relationships | 2026-04-12 | 2026-04-15 | -7 | 2026-04-15 | 1
Tested complete server installation process | 2026-04-14 | 2026-04-15 | -7 | 2026-04-15 | 1
Updated the database on the server | 2026-04-14 | 2026-04-15 | -7 | 2026-04-15 | 1
worked with carson to get last minute kinks out (automatic backups) | 2026-04-16 | 2026-04-16 | -6 | 2026-04-16 | 1
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Lukas White
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
Weekly Meeting | 2026-01-22 | 2026-01-22 | -90 | 2026-01-22 | 1
Week of January 26, 2026
Weekly Meeting | 2026-01-28 | 2026-01-28 | -84 | 2026-01-28 | 1
Created Demo Video | 2026-01-22 | 2026-02-05 | 4 | 2026-01-30 | 1
Week of February 1, 2026
Attended meeting 3 | 2026-02-03 | 2026-02-03 | -6 | 2026-02-03 | 1
Week of February 9, 2026
Attended meeting 3 | 2026-02-09 | 2026-02-09 | -72 |  | -1 | Meeting date was changed too late, scheduling confliction could not be resolved
Week of February 15, 2026
Attended meeting 4 | 2026-02-19 | 2026-02-19 | -9 | 2026-02-19 | 1
Assigned Sprint 2 Tasks | 2026-02-19 | 2026-02-19 | -9 | 2026-02-19 | 1
Test DropdownComponents.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test RoundedDropdown.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test DataBox.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test EmptyTextbox.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test EmptyTextboxUnseen.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test Password.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test PasswordUnseen.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test Searchbox.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Test UsernameTextbox.cs | 2026-02-19 | 2026-03-09 | 9 |  | -1
Week of February 22, 2026
Weekly Meeting | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Fix Github merge issue | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Week of March 1, 2026
Weekly Meeting | 2026-03-05 | 2026-03-05 | -12 |  | -1 | Non-mandatory meeting during spring break.
Week of March 8, 2026
Test CalendarHelpers.cs | 2026-03-12 | 2026-03-26 | 8 |  | -1
Test HomeHelper.cs | 2026-03-12 | 2026-03-26 | 8 |  | -1
Test PeopleWithHomesHelper.cs | 2026-03-12 | 2026-03-26 | 8 |  | -1
Test PetWithHomesHelper.cs | 2026-03-12 | 2026-03-26 | 8 |  | -1 | Will update doc to be more specific with these later when learn more
Test Forms | 2026-03-12 | 2026-03-26 | 8 |  | -1
Test PetForms | 2026-03-12 | 2026-03-26 | 8 |  | -1
Test DropdownComponents | 2026-03-12 | 2026-03-26 | 8 |  | -1
Test Text_Components | 2026-03-12 | 2026-03-26 | 8 |  | -1
Week of March 16, 2026
Weekly Meeting | 2026-03-05 | 2026-03-22 | -13 | 2026-03-22 | 1 | Attended via call
Continue Testing | 2026-03-16 | 2026-03-22 | -13 | 2026-03-22 | 1
Database Requirement Testing | 2026-03-19 | 2026-04-09 | 5 | 2026-04-03 | 1
Week of March 23, 2026
Finish Sprint 3/4 | 2026-03-23 | 2026-03-26 | -9 | 2026-03-26 | 1
Weekly Meeting | 2026-03-26 | 2026-03-26 | -9 | 2026-03-26 | 1
Database setup guide review
Week of March 30, 2026
Continue Testing | 2026-03-23 | 2026-03-26 | -9 | 2026-03-26 | 1
Github Pull Requests | 2026-04-01 | 2026-04-01 | -3 | 2026-04-01 | 1
Week of April 6, 2026
Continue Testing | 2026-04-06 | 2026-04-12 | -10 | 2026-04-12 | 1
Github Pull Requests | 2026-04-06 | 2026-04-12 | -10 | 2026-04-12 | 1
Week of April 13, 2026
Continue Testing | 2026-04-13 | 2026-04-16 | -6 | 2026-04-16 | 1
Github Pull Requests | 2026-04-13 | 2026-04-16 | -6 | 2026-04-16 | 1
Test Databate Start up | 2026-04-12 | 2026-04-14 | -8 | 2026-04-14 | 1
Peer Reviews | 2026-04-14 | 2026-04-21 | -1 | 2026-04-19 | 1
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Max Yaw
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
Weekly Meeting | 2026-01-22 | 2026-01-22 | -90 | 2026-01-22 | 1
Week of January 25th
Weekly Meeting | 2026-01-29 | 2026-01-29 | -2 | 2026-01-29 | 1
Week of february 1st
Weekly Meeting | 2026-02-01 | 2026-02-01 | -7 | 2026-02-01 | 1
Pet, Surgery, Prevention Unit Testing | 2026-02-03 | 2026-02-07 | -7 | 2026-02-05 | 1
Week of February 9th
Weekly Meeting | 2026-02-09 | 2026-02-09 | -7 | 2026-02-09 | 1
Week of February 16
Weekly Meeting | 2/19/026 | 2026-02-19 | -9 | 2026-02-19 | 1
Week of February 23
Weekly Meeting | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Created test and manual tested checkbox | 2026-02-28 | 2026-02-28 | 0 | 2026-02-28 | 1
Investigated WinForms UI testing limitations and documented blockers by current code behind structure | 2026-02-26 | 2026-02-26 | -2 | 2026-02-26 | 1
Week of March 1
Weekly meeting (sprint 2) | 2026-03-05 | 2026-03-05 | -12 | 2026-03-05 | 1
Comlpleted unit tests for all common components and manual tested | 2026-03-06 | 2026-03-06 | -11 | 2026-03-06 | 1
Completed Unit tests for all menu side bar components and manual tested | 2026-03-06 | 2026-03-06 | -11 | 2026-03-06 | 1
Completed manual testing for PetMain and CreatePet forms | 2026-03-06 | 2026-03-06 | -11 | 2026-03-06 | 1
Week of March 8
Weeky Meeting | 2026-03-19 | 2026-03-19 | -3 | 2026-03-19 | 1
sql injection tests | 2026-03-19 | 2026-03-19 | -3 | 2026-03-19 | 1
started helpers | 2026-03-19 | 2026-03-19 | -3 | 2026-03-19 | 1
Week of March 16
Finished 6 helper file tests | 2026-03-23 | 2026-03-23 | -12 | 2026-03-23 | 1
Attended weekly meeting | 2026-03-23 | 2026-03-23 | -12 | 2026-03-23 | 1
Started db requirement testing (10) | 2026-03-23 | 2026-03-23 | -12 | 2026-03-23 | 1
Week of March 23
DB requirement testing | 2026-03-26 | 2026-03-26 | -27 | 2026-03-26 | 1
Weekyl meeting | 2026-03-26 | 2026-03-26 | -27 | 2026-03-26 | 1
Week of March 30
DB requirements testing. Restested all already tested on new code and finished the ones I could | 2026-04-02 | 2026-04-02 | -20 | 2026-04-02 | 1
Week of April 6
DB requirements testing. Restested all already tested on new code and finished the ones I could | 2026-04-08 | 2026-04-08 | -14 | 2026-04-08 | 1
Week of April 13
Nothing here finished all testing over weekend
Formulas:
Days Left = DAYS([Due Date],TODAY())

## Team Member Name
Task Name | Start Date | Due Date | Days Left | End Date | Complete? | Group Lead Comments
Week of January 18, 226
|  |  | -46134 |  | -1
Formulas:
Days Left = DAYS([Due Date],TODAY())